## Program 2021
Element |  |  |  | Program 2015
Management Commitment |  |  |  | Update all Top Management Policy (Review, Update if necessary, Re-sign), Management Walk Through Plan and Realized, Update HSE Pogram, Update HSE Objective 2015, Update HSE Golden Rules, Update HSE Principal of Work
Resources Structure & Responsibility |  |  |  | Update Organization Chart (Structrure Organization PT SES, Structure Organization HSE, HSE Commite), update resposibility and jobdesc
Legal Business Compliance |  |  |  | Find for Relevant Legal Reference and evaluation of compliance
Risk Management |  |  |  | Update Risk Assessment, JSA Field and Office, Risk Assessment compliance with local legal regulation
Operational Control |  |  |  | Record and Monitoring PPE stock and control, record Hand Over PPE, design and instal warning sign at office and warehouse, work permit at warehouse/office, updating and review SIKA, Occupational health program, maintenance equipment (Forklift), laboratory equipment (supervisi or collecting certificate for evidence maintenance equipment), waste management, contractor safety requirement.
SH&E Activity Plan 2021
Element |  | PIC | Y/N/N/A | Schedule
|  |  |  | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2021 & Golden Rules | SH&E, BOD | bar: Schedule Jan
- | Review and Update SH&E Activity Plan | SH&E | bar: Schedule Jan
- | SH&E Policy, Objectives and SH&E Activity Plan Socialization | SH&E | bar: Schedule Feb
- | Management Walk Through | Log, Opr, SH&E, BOD |  | OM/MC | Dir Ops | LM | SM | Dir | OM/MC | Dir Ops | LM | SM | Dir | OM/MC | Dir Ops
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC | SH&E, Opr, Lab, Log | bar: Schedule Feb
- | Review of Criteria Risk Assessment | SH&E | bar: Schedule Mar
- | Evaluation Risk Assessment Compliance with Local Legal Regulation | SH&E | bar: Schedule Mar
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary) | SH&E, Opr, Lab, Log | bar: Schedule Mar
- | Review and Update MSDS | SH&E, Opr, Log | bar: Schedule Apr
3. Management of Change
- | Conduct Management of Change (If necessary) | Opr, Log, Lab, SH&E
- | Review and Update Management of Change (If necessary) | Opr, Log, Lab, SH&E | bar: Schedule June
- | Evaluation of MoC (If necessary) | Opr, Log, Lab, SH&E | bar: Schedule June to Schedule July
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | SH&E, Legal | bar: Schedule Mar; Schedule Sept
- | Evaluation of Compliance Local & International Legal Regulation | SH&E, Legal | bar: Schedule Mar; Schedule Sept
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI | HR | bar: Schedule Jan
- | Review and Update Structure Organization of SH&E | SH&E | bar: Schedule Jan
- | Review and Update Organization SH&E Committee | SH&E | bar: Schedule Jan
- | Update Jobdesc and Responsibility | HR | bar: Schedule Jan
6. Training & Competency
- | Conduct SH&E Induction for new employee | SH&E
- | Update Training Schedule 2021 | HR, SH&E | bar: Schedule Feb
- | Update Training Matrix & Training Need Analysis 2021 | HR, SH&E | bar: Schedule Feb
7. Communications
- | Conduct SH&E Monthly Meeting | SH&E
- | Conduct SH&E Committee Meeting | SH&E | bar: Schedule Apr; Schedule July; Schedule Oct
- | Review and Update OSH Sign or Label | SH&E | bar: Schedule Apr; Schedule Oct
- | Conduct SH&E Toolbox Meeting | Opr, Log, Lab
- | Conduct Safety Talk (if necessary) | Opr, Log, Lab
- | Review and Revise SH&E Handbook | SH&E | bar: Schedule Apr
- | Distribution & Socialization SH&E HandBook | SH&E | bar: Schedule May to Schedule June
- | Updated SH&E Allert (Posted at HSE Board) | SH&E | bar: Schedule Mar
- | Conduct SH&E Buletin and SH&E Campaign | SH&E | bar: Schedule Mar
- | Conduct SH&E reward Program | SH&E
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update Procedure & Work Instruction | SH&E | bar: Schedule Feb to Schedule Mar
- | Review and Update Internal Document & External Document | SH&E | bar: Schedule May to Schedule June
- | Prepare & Update CSMS and SIKA Document (if Necessary) | SH&E
Records
- | Review, Screening & Filing Documents | SH&E
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE Related) | SH&E | bar: Schedule Mar to Schedule Apr
- | Review and Update PPE Stock and Control | SH&E
- | Update PPE Record | SH&E
- | Conduct of Work Permit at warehouse, Lab & office (if Necessary) | Opr, Log, Lab
- | Conduct of Waste management, If Necessary | Log, Opr, SH&E
Maintenance Equipment:
- | Review Maintenance Schedule of Laboratory Equipment | Lab | bar: Schedule Feb; Schedule May; Schedule Aug; Schedule Nov
- | Review and Update Maintenance Schedule of Light Vehicle | Log, HR | bar: Schedule Mar; Schedule June; Schedule Sept; Schedule Dec
10. Emergency Response Plan
- | Review and Update ERP Program | SH&E | bar: Schedule Apr
- | Review and Update Emergency Response Team | SH&E | bar: Schedule Apr
- | Conduct Drill at Office and Warehouse | All Dept | bar: Schedule Sept
- | Review & evaluation of Emergency Drill | SH&E | bar: Schedule Sept
- | Evaluation of Emergency Equipment | SH&E | bar: Schedule Aug
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard | SH&E | bar: Schedule July
11. Performance
- | Review and Record SH&E Performance Every Month | SH&E
- | Review and Update SH&E Monthly Report | SH&E
- | Evaluation SH&E Performance | SH&E
- | Review and Update Leading & Lagging Indicator | SH&E
12. Monitoring Measurement & Evaluation
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature) | SH&E | bar: Schedule May
- | Conduct Measurement of Industrial Hygiene | SH&E | bar: Schedule June; Schedule Dec
- | Review and Update MCU Schedule | HR | bar: Schedule Jan; Schedule June; Schedule Dec
- | Conduct MCU include Audiometry, Alcohol & Drugs Test (as per schedule) | HR
- | Evaluation of MCU Result (as per schedule) | HR, SH&E
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action
- | Create the Investigation Team | SH&E | bar: Schedule Jan
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur) | Related Dept
- | Review and update Incident and Accident Investigation Report (as per Incident occur) | SH&E
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur) | Related Dept
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur) | Related Dept
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur) | SH&E
- | Conduct Observation Card Program | All Dept
- | Record and evaluation observation Card | SH&E
14. Inspection & Internal Audit
Inspection
- | Review and Update Inspection Schedule | SH&E | bar: Schedule Jan
- | Conduct Inspection Vehicle for Subcon | Log
- | Conduct Operation Vehicle (Pre-Trip Inspection) | Log, HR
- | Conduct General Inspection at Office, Lab and Warehouse | SH&E | bar: Schedule Apr; Schedule July; Schedule Oct
- | Conduct PPE Inspection | SH&E
Audit
- | Review and Update Schedule of Internal Audit Include Auditor Team | SH&E | bar: Schedule July
- | Conduct Audit Internal | Related Dept | bar: Schedule Oct
- | Review & Evaluation Internal Audit Result & Record it | SH&E | bar: Schedule Oct
- | Conduct Audit Subcontractor | Proc, SH&E | bar: Schedule June
15. Management Review
- | Review and Update Management Review Schedule | SH&E | bar: Schedule May
- | Conduct Management Review | All Dept | bar: Schedule Nov
- | Evaluation of Management Review Result | All Dept | bar: Schedule Dec
- | Review and Evaluation SH&E Activity Plan 2021 | SH&E | bar: Schedule Dec
- | Conduct Corrective Action from Management Review Result (End of Year) | SH&E | bar: Schedule Dec
Jakarta, January 19th 2021
| Prepared by |  |  | Schedule Apr: Reviewed by; Schedule Nov: Approved by
| Sianinda Pasol |  |  | Schedule Apr: Yosep Dody; Schedule Nov: Junius Natalim
| SH&E Officer |  |  | Schedule Apr: SH&E Manager; Schedule Nov: Director

## Jan - June (hidden)
Element |  | Program 2015
Management Commitment |  | Update all Top Management Policy (Review, Update if necessary, Re-sign), Management Walk Through Plan and Realized, Update HSE Pogram, Update HSE Objective 2015, Update HSE Golden Rules, Update HSE Principal of Work
Resources Structure & Responsibility |  | Update Organization Chart (Structrure Organization PT SES, Structure Organization HSE, HSE Commite), update resposibility and jobdesc
Legal Business Compliance |  | Find for Relevant Legal Reference and evaluation of compliance
Risk Management |  | Update Risk Assessment, JSA Field and Office, Risk Assessment compliance with local legal regulation
Operational Control |  | Record and Monitoring PPE stock and control, record Hand Over PPE, design and instal warning sign at office and warehouse, work permit at warehouse/office, updating and review SIKA, Occupational health program, maintenance equipment (Forklift), laboratory equipment (supervisi or collecting certificate for evidence maintenance equipment), waste management, contractor safety requirement.
SH&E Activity Plan 2020
Element |  | Schedule | [5 empty] | Done
|  | Jan | Feb | Mar | Apr | May | June | Y/N
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2018 & Golden Rules | bar: Schedule Jan
- | Review and Update SH&E Activity Plan | bar: Schedule Jan
- | SH&E Policy, Objectives & SH&E Activity Plan Socialization | bar: Schedule Feb
- | Management Walk Through | OM/MC | SM | LM | OM/MC | Dir Ops | Dir
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC | bar: Schedule Mar
- | Review of Criteria Risk Assessment | bar: Schedule Mar
- | Evaluation Risk Assessment Compliance with Local Legal Regulation | bar: Schedule Mar
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary) | bar: Schedule Mar
- | Review and Update MSDS | bar: Schedule Apr
3. Management of Change
- | Conduct Management of Change
- | Review and Update Management of Change | bar: Schedule June
- | Evaluation of MoC | bar: Schedule June
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | bar: Schedule Mar
- | Evaluation of Compliance Local & International Legal Regulation | bar: Schedule Mar
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI | bar: Schedule Jan
- | Review and Update Structure Organization of SH&E | bar: Schedule Jan
- | Review and Update Organization SH&E Commite | bar: Schedule Jan
- | Update Jobdesc and Responsibility | bar: Schedule Jan
6. Training & Competency
- | Conduct SH&E Induction for new employee
- | Update Training Schedule 2019 | bar: Schedule Feb
- | Update Training Matrix & Training Need Analysis 2019 | bar: Schedule Feb
7. Communications
- | Conduct SH&E Monthly Meeting
- | Conduct SH&E Committee Meeting | bar: Schedule Apr
- | Review and Update OHS Sign or Label | bar: Schedule Apr
- | Conduct SH&E Toolbox Meeting
- | Conduct Safety Talk (if necessary)
- | Review and Revise SH&E Handbook | bar: Schedule Feb
- | Distribution & Socialization SH&E HandBook | bar: Schedule Mar; Schedule June
- | Updated SH&E Alert (Templated at HSE Board) | bar: Schedule Mar
- | Conduct SH&E Buletin and SH&E Campaign | bar: Schedule Mar
- | Conduct SH&E reward Program
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update SH&E Policy, Procedure & Work Instruction | bar: Schedule Mar to Schedule Apr
- | Review and Update Internal document & external document | bar: Schedule May to Schedule June
- | Prepare & update CSMS and SIKA document (if Necessary)
- | Review and Update document, if necessary
Records
- | Review, Screening & Filing Documents
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE related) | bar: Schedule Mar to Schedule Apr
- | Review and Update PPE Stock and Control
- | Update PPE Record
- | Conduct of Work permit at warehouse, Lab & office (if Necessary)
- | Conduct of Waste management, If necessary
Maintenance equipment:
- | Update Maintenance Schedule of Forklift
- | Review Maintenance Schedule of Laboratory equipment | bar: Schedule Feb; Schedule May
- | Review and Update Maintenance Schedule of Light Vehicle | bar: Schedule Mar; Schedule June
10. Emergency Response Plan
- | Review and Update ERP Program | bar: Schedule Feb
- | Review and Update Emergency Response Team | bar: Schedule Feb
- | Conduct Drill at Office and Warehouse
- | Review & evaluation of Emergency Drill
- | Evaluation of Emergency Equipment
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard
11. Performance
- | Review and Record SH&E Performance every month
- | Review and Update SH&E Monthly report
- | Evaluation SH&E Performance
- | Review and Update Leading & Lagging Indicator | bar: Schedule Jan; Schedule June
12. Monitoring Measurement & Evaluation
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature) | bar: Schedule May
- | Conduct Measurement of Industrial Hygiene | bar: Schedule June
- | Review and Update MCU Schedule | bar: Schedule Jan; Schedule June
- | Conduct MCU include audiometry, Alcohol & Drugs Test (as per schedule)
- | Evaluation of MCU Result (as per schedule)
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action
- | Create the Investigation Team | bar: Schedule Jan
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur)
- | Review and update Incident and Accident Investigation Report (as per Incident occur)
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur)
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur)
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur)
- | Conduct Observation Card Program
- | Record and evaluation observation card
14. Inspection & Internal Audit
Inspection
- | Review and Update Inspection Schedule | bar: Schedule Jan; Schedule May
- | Conduct Inspection Vehicle for Subcon
- | Conduct Operation Vehicle (Pre-Trip Inspection)
- | Conduct General Inspection at Office, Lab and Warehouse | bar: Schedule Apr
- | Conduct PPE Inspection
Audit
- | Review and Update Schedule of Internal Audit Include Auditor Team
- | Conduct Audit Internal
- | Review & Evaluation Internal Audit Result & Record it
- | Conduct Audit Subcontractor | bar: Schedule June
15. Management Review
- | Review and Update Management Review Schedule | bar: Schedule Apr
- | Conduct Management Review
- | Evaluation of Management Review Result
- | Review and Evaluation HSE Activity Plan 2018
- | Conduct Corrective Action from Management Review Result (End of Year)
| Total of Action Item Program (jan-august) | Schedule Jan: 0
| Quantity of Month (until august) | Schedule Jan: 0
| Total of Compliance Action Item Program (until August) | Schedule Jan: #DIV/0!
Jakarta, 29 January 2019
| Prepared by | Schedule Apr: Reviewed by
| Leni Andani | Schedule Apr: Yosep Dody
| SH&E Officer | Schedule Apr: SH&E Manager

## Jul - Dec (hidden)
Element
Management Commitment
Resources Structure & Responsibility
Legal Business Compliance
Risk Management
Operational Control
SH&E Activity Plan 2019
Element | [7 empty] | Done
|  | July | Aug | Sept | Oct | Nov | Dec | Y/N
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2018 & Golden Rules
- | Review and Update SH&E Activity Plan
- | SH&E Policy, Objectives & SH&E Activity Plan Socialization
- | Management Walk Through | MC | SM | LM | OM | Dir Ops | Dir
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC
- | Review of Criteria Risk Assessment
- | Evaluation Risk Assessment Compliance with Local Legal Regulation
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary)
- | Review and Update MSDS
3. Management of Change
- | Conduct Management of Change
- | Review and Update Management of Change
- | Evaluation of MoC | bar: July
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | bar: Sept
- | Evaluation of Compliance Local & International Legal Regulation | bar: Sept
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI
- | Review and Update Structure Organization of SH&E
- | Review and Update Organization SH&E Commite
- | Update Jobdesc and Responsibility
6. Training & Competency
- | Conduct SH&E Induction for new employee
- | Update Training Schedule 2019
- | Update Training Matrix & Training Need Analysis 2019
7. Communications
- | Conduct SH&E Monthly Meeting
- | Conduct SH&E Committee Meeting | bar: July; Oct
- | Review and Update OHS Sign or Label | bar: Oct
- | Conduct SH&E Toolbox Meeting
- | Conduct Safety Talk (if necessary)
- | Review and Revise SH&E Handbook
- | Distribution & Socialization SH&E HandBook
- | Updated SH&E Alert (Templated at HSE Board)
- | Conduct SH&E Buletin and SH&E Campaign
- | Conduct SH&E reward Program
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update SH&E Policy, Procedure & Work Instruction
- | Review and Update Internal document & external document
- | Prepare & update CSMS and SIKA document (if Necessary)
- | Review and Update document, if necessary
Records
- | Review, Screening & Filing Documents
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE related)
- | Review and Update PPE Stock and Control
- | Update PPE Record
- | Conduct of Work permit at warehouse, Lab & office (if Necessary)
- | Conduct of Waste management, If necessary
Maintenance equipment:
- | Update Maintenance Schedule of Forklift
- | Review Maintenance Schedule of Laboratory equipment | bar: Aug; Nov
- | Review and Update Maintenance Schedule of Light Vehicle | bar: Sept; Dec
10. Emergency Response Plan
- | Review and Update ERP Program
- | Review and Update Emergency Response Team
- | Conduct Drill at Office and Warehouse | bar: July
- | Review & evaluation of Emergency Drill | bar: Aug
- | Evaluation of Emergency Equipment | bar: Aug
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard | bar: Aug
11. Performance
- | Review and Record SH&E Performance every month
- | Review and Update SH&E Monthly report
- | Evaluation SH&E Performance
- | Review and Update Leading & Lagging Indicator | bar: Nov
12. Monitoring Measurement & Evaluation
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature)
- | Conduct Measurement of Industrial Hygiene | bar: Dec
- | Review and Update MCU Schedule | bar: Dec
- | Conduct MCU include audiometry, Alcohol & Drugs Test (as per schedule)
- | Evaluation of MCU Result (as per schedule)
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action
- | Create the Investigation Team
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur)
- | Review and update Incident and Accident Investigation Report (as per Incident occur)
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur)
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur)
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur)
- | Conduct Observation Card Program
- | Record and evaluation observation card
14. Inspection & Internal Audit
Inspection
- | Review and Update Inspection Schedule | bar: Sept
- | Conduct Inspection Vehicle for Subcon
- | Conduct Operation Vehicle (Pre-Trip Inspection)
- | Conduct General Inspection at Office, Lab and Warehouse | bar: July; Oct
- | Conduct PPE Inspection
Audit
- | Review and Update Schedule of Internal Audit Include Auditor Team | bar: July
- | Conduct Audit Internal | bar: Oct
- | Review & Evaluation Internal Audit Result & Record it | bar: Oct
- | Conduct Audit Subcontractor
15. Management Review
- | Review and Update Management Review Schedule
- | Conduct Management Review | bar: Nov
- | Evaluation of Management Review Result | bar: Dec
- | Review and Evaluation HSE Activity Plan 2018 | bar: Dec
- | Conduct Corrective Action from Management Review Result (End of Year) | bar: Dec
Total of Action Item Program (jan-august)
Quantity of Month (until august)
Total of Compliance Action Item Program (until August)
Jakarta, 29 January 2019
| Prepared by | Nov: Approved by
| Leni Andani | Nov: Junius Natalim
| SH&E Officer | Nov: Director

## Checklist Program (hidden)
Element |  |  |  |  | Program 2014
Management Commitment |  |  |  |  | Update all Top Management Policy (Review, Update if necessary, Re-sign), Management Walk Through Plan and Realized, Update HSE Pogram, Update HSE Objective 2014, Update HSE Golden Rules, Update HSE Principal of Work
Resources Structure & Responsibility |  |  |  |  | Update Organization Chart (Structrure Organization PT SES, Structure Organization HSE, HSE Commite), update resposibility and jobdesc
Legal Business Compliance |  |  |  |  | Find for Relevant Legal Reference and evaluation of compliance
Risk Management |  |  |  |  | Update Risk Assessment, JSA Field and Office, Risk Assessment compliance with local legal regulation
Operational Control |  |  |  |  | Record and Monitoring PPE stock and control, record Hand Over PPE, design and instal warning sign at office and warehouse, work permit at warehouse/office, updating and review SIKA, Occupational health program, maintenance equipment (Forklift), laboratory equipment (supervisi or collecting certificate for evidence maintenance equipment), waste management, contractor safety requirement.
Element |  |  |  |  | Schedule
Management Commitment |  | Jan | Feb | Mar | Apr | May | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | May | Done Y/N | Remark
Review and Update if necessary:
- | Review and Update SHE Policy, Objective 2016 & Golden Rules | bar: Schedule May
- | Review and Update SHE Activity Plan | bar: Schedule May
- | SHE Policy & Objective & Socialization Program | bar: Schedule May
- | Management Walk Through | bar: Schedule May
Resources Structure & Responsibility
Review and Update if necessary:
- | Review and Update Structure Organization Chart PT SES | bar: Schedule May
- | Review and Update Structure Organization of SHE | bar: Schedule May
- | Review and Update Organization SHE Commite | bar: Schedule May
- | Update Jobdesc and Responsibility | bar: Schedule May
Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation
- | Evaluation of Compliance Local & International Legal Regulation
Risk Management
Update if necessary:
- | Review and Update HIRADC
- | Review of Criteria Risk Assessment
- | Evaluation Risk Assessment Compliance with Local Legal Regulation
- | Conduct or Update JSA at Field, Warehouse, Lab & Office (if Necessary)
- | Review and Update MSDS
Management of Change
- | Conduct Management of Change
- | Review and Update Management of Change
- | Evaluation of MoC
Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE related)
- | Review and Update PPE Stock and Control
- | Update PPE Record
- | Conduct of Work permit at warehouse, Lab & office (if Necessary)
- | Conduct of Waste management
Maintenance equipment:
- | Update Maintenance Schedule of Forklift
- | Review Maintenance Schedule of Laboratory equipment
-
- | Review and Update Maintenance Schedule of Light Vehicle
- | Review Maintenance Schedule of Warehouse Facility
Training & Competency
- | Conduct SHE Induction for new employee | bar: Jan
- | Update Training Schedule 2016
- | Update Training Matrix & Training Need Analysis 2016
Communication & Information
- | Conduct SHE Monthly Meeting | bar: Jan
- | Review and Update OHS Sign or Label
- | Conduct SHE Toolbox Meeting | bar: Jan
- | Conduct Safety Talk (if necessary)
- | Distribution & Socialization SHE HandBook
- | Updated SHE Alert (Templated at HSE Board)
- | Conduct SHE Buletin and SHE Campaign
- | Conduct HSE reward Program
Emergency Response Plan
- | Review and Update ERP Program
- | Review and Update Emergency Response Team
- | Conduct Drill at Office and Warehouse
- | Review & evaluation of Emergency Drill
- | Evaluation of Emergency Equipment
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard
Documentation, Control of Document & Records
Documentation & Control
- | Review and Update SHE Policy, Procedure & Work Instruction
- | Review and Update Internal document & external document
- | Prepare & update CSMS and SIKA document (if Necessary)
- | Review and Update document, if necessary
Records
- | Review, Screening & Filing Documents | bar: Jan
Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action
- | Create the Investigation Team
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur)
- | Review and update Incident and Accident Investigation Report (as per Incident occur)
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur)
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur)
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur)
- | Conduct Observation Card Program
- | Record and evaluation observation card
Monitoring Measurement & Evaluation
Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature)
Conduct Measurement of Industrial Hygiene
- | Review and Update MCU Schedule
- | Conduct MCU include audiometry, Alcohol & Drugs Test (as per schedule)
- | Evaluation of MCU Result (as per schedule)
Performance
- | Review and Record SHE Performance every month
- | Review and Update SHE Monthly report
- | Evaluation SHE Performance
- | Review and Update Leading & Lagging Indicator
Inspection & Audit
Inspection
- | Review and Update Inspection Schedule
- | Conduct Inspection Vehicle for Subcon
- | Conduct Operation Vehicle (Pre-Trip Inspection)
- | Conduct General Inspection at Office, Lab and Warehouse
- | Conduct PPE Inspection
Audit
- | Review and Update Schedule of Internal Audit Include Auditor Team
- | Conduct Audit Internal
- | Review & Evaluation Internal Audit Result & Record it
- | Conduct Audit Subcontractor
Management Review
- | Review and Update Management Review Schedule
- | Conduct Management Review
- | Evaluation of Management Review Result
- | Review and Evaluation HSE Activity Plan 2016
- | Conduct Corrective Action from Management Review Result (End of Year)

## Jan
Element |  |  |  | Program 2015
Management Commitment |  |  |  | Update all Top Management Policy (Review, Update if necessary, Re-sign), Management Walk Through Plan and Realized, Update HSE Pogram, Update HSE Objective 2015, Update HSE Golden Rules, Update HSE Principal of Work
Resources Structure & Responsibility |  |  |  | Update Organization Chart (Structrure Organization PT SES, Structure Organization HSE, HSE Commite), update resposibility and jobdesc
Legal Business Compliance |  |  |  | Find for Relevant Legal Reference and evaluation of compliance
Risk Management |  |  |  | Update Risk Assessment, JSA Field and Office, Risk Assessment compliance with local legal regulation
Operational Control |  |  |  | Record and Monitoring PPE stock and control, record Hand Over PPE, design and instal warning sign at office and warehouse, work permit at warehouse/office, updating and review SIKA, Occupational health program, maintenance equipment (Forklift), laboratory equipment (supervisi or collecting certificate for evidence maintenance equipment), waste management, contractor safety requirement.
SH&E Activity Plan 2020
Element |  | PIC | Y/N/N/A | Jan
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2019 & Golden Rules | SH&E, BOD
- | Review and Update SH&E Activity Plan | SH&E
- | SH&E Policy, Objectives and SH&E Activity Plan Socialization | SH&E
- | Management Walk Through | Log, Opr, SH&E, BOD |  | OM/MC
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC | SH&E, Opr, Lab, Log
- | Review of Criteria Risk Assessment | SH&E
- | Evaluation Risk Assessment Compliance with Local Legal Regulation | SH&E
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary) | SH&E, Opr, Lab, Log
- | Review and Update MSDS | SH&E, Opr, Log
3. Management of Change
- | Conduct Management of Change | Opr, Log, Lab, SH&E
- | Review and Update Management of Change | Opr, Log, Lab, SH&E
- | Evaluation of MoC | Opr, Log, Lab, SH&E
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | SH&E, Legal
- | Evaluation of Compliance Local & International Legal Regulation | SH&E, Legal
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI | HR
- | Review and Update Structure Organization of SH&E | SH&E
- | Review and Update Organization SH&E Committee | SH&E
- | Update Jobdesc and Responsibility | HR
6. Training & Competency
- | Conduct SH&E Induction for new employee | SH&E
- | Update Training Schedule 2019 | HR
- | Update Training Matrix & Training Need Analysis 2019 | HR
7. Communications
- | Conduct SH&E Monthly Meeting | SH&E
- | Conduct SH&E Committee Meeting | SH&E
- | Review and Update OSH Sign or Label | SH&E
- | Conduct SH&E Toolbox Meeting | Opr, Log, Lab
- | Conduct Safety Talk (if necessary) | Opr, Log, Lab
- | Review and Revise SH&E Handbook | SH&E
- | Distribution & Socialization SH&E HandBook | SH&E
- | Updated SH&E Allert (Posted at HSE Board) | SH&E
- | Conduct SH&E Buletin and SH&E Campaign | SH&E
- | Conduct SH&E reward Program | SH&E
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update SH&E Policy, Procedure & Work Instruction | SH&E
- | Review and Update Internal Document & External Document | SH&E
- | Prepare & Update CSMS and SIKA Document (if Necessary) | SH&E
- | Review and Update Document, if Necessary | SH&E
Records
- | Review, Screening & Filing Documents | SH&E
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE Related) | SH&E
- | Review and Update PPE Stock and Control | SH&E
- | Update PPE Record | SH&E
- | Conduct of Work Permit at warehouse, Lab & office (if Necessary) | Opr, Log, Lab
- | Conduct of Waste management, If Necessary | Log, Opr, SH&E
Maintenance Equipment:
- | Update Maintenance Schedule of Forklift | Log
- | Review Maintenance Schedule of Laboratory Equipment | Lab
- | Review and Update Maintenance Schedule of Light Vehicle | Log, HR
10. Emergency Response Plan
- | Review and Update ERP Program | SH&E
- | Review and Update Emergency Response Team | SH&E
- | Conduct Drill at Office and Warehouse | All Dept
- | Review & evaluation of Emergency Drill | SH&E
- | Evaluation of Emergency Equipment | SH&E
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard | SH&E
11. Performance
- | Review and Record SH&E Performance Every Month | SH&E
- | Review and Update SH&E Monthly Report | SH&E
- | Evaluation SH&E Performance | SH&E
- | Review and Update Leading & Lagging Indicator | SH&E
12. Monitoring Measurement & Evaluation
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature) | SH&E
- | Conduct Measurement of Industrial Hygiene | SH&E
- | Review and Update MCU Schedule | HR
- | Conduct MCU include Audiometry, Alcohol & Drugs Test (as per schedule) | HR
- | Evaluation of MCU Result (as per schedule) | HR, SH&E
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action
- | Create the Investigation Team | SH&E
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur) | Related Dept
- | Review and update Incident and Accident Investigation Report (as per Incident occur) | SH&E
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur) | Related Dept
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur) | Related Dept
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur) | SH&E
- | Conduct Observation Card Program | All Dept
- | Record and evaluation observation Card | SH&E
14. Inspection & Internal Audit
Inspection
- | Review and Update Inspection Schedule | SH&E
- | Conduct Inspection Vehicle for Subcon | Log
- | Conduct Operation Vehicle (Pre-Trip Inspection) | Log, HR
- | Conduct General Inspection at Office, Lab and Warehouse | SH&E
- | Conduct PPE Inspection | SH&E
Audit
- | Review and Update Schedule of Internal Audit Include Auditor Team | SH&E
- | Conduct Audit Internal | Related Dept
- | Review & Evaluation Internal Audit Result & Record it | SH&E
- | Conduct Audit Subcontractor | Proc, SH&E
15. Management Review
- | Review and Update Management Review Schedule | SH&E
- | Conduct Management Review | All Dept
- | Evaluation of Management Review Result | All Dept
- | Review and Evaluation SH&E Activity Plan 2018 | SH&E
- | Conduct Corrective Action from Management Review Result (End of Year) | SH&E
| Total of Action Item Program (Jan) |  |  | 0
| Total of Compliance Action Item Program |  |  | #REF!
Jakarta, 29 January 2019
Prepared by
Leni Andani
SH&E Officer

## Feb
Element
Management Commitment
Resources Structure & Responsibility
Legal Business Compliance
Risk Management
Operational Control
SH&E Activity Plan 2020
Element |  | PIC | Y/N/N/A | Feb
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2018 & Golden Rules | SH&E, BOD
- | Review and Update SH&E Activity Plan | SH&E
- | SH&E Policy, Objectives & SH&E Activity Plan Socialization | SH&E
- | Management Walk Through | Log, Opr, SH&E, BOD |  | OM/MC
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC | SH&E, Opr, Lab, Log
- | Review of Criteria Risk Assessment | SH&E
- | Evaluation Risk Assessment Compliance with Local Legal Regulation | SH&E
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary) | SH&E, Opr, Lab, Log
- | Review and Update MSDS | SH&E, Opr, Log
3. Management of Change
- | Conduct Management of Change | Opr, Log, Lab, SH&E
- | Review and Update Management of Change | Opr, Log, Lab, SH&E
- | Evaluation of MoC | Opr, Log, Lab, SH&E
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | SH&E, Legal
- | Evaluation of Compliance Local & International Legal Regulation | SH&E, Legal
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI | HR
- | Review and Update Structure Organization of SH&E | SH&E
- | Review and Update Organization SH&E Commite | SH&E
- | Update Jobdesc and Responsibility | HR
6. Training & Competency
- | Conduct SH&E Induction for new employee | SH&E
- | Update Training Schedule 2020 | HR
- | Update Training Matrix & Training Need Analysis 2020 | HR
7. Communications
- | Conduct SH&E Monthly Meeting | SH&E
- | Conduct SH&E Committee Meeting | SH&E
- | Review and Update OHS Sign or Label | SH&E
- | Conduct SH&E Toolbox Meeting | Opr, Log, Lab
- | Conduct Safety Talk (if necessary) | Opr, Log, Lab
- | Review and Revise SH&E Handbook | SH&E
- | Distribution & Socialization SH&E HandBook | SH&E
- | Updated SH&E Alert (Templated at HSE Board) | SH&E
- | Conduct SH&E Buletin and SH&E Campaign | SH&E
- | Conduct SH&E reward Program | SH&E
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update Procedure & Work Instruction | SH&E
- | Review and Update Internal document & external document | SH&E
- | Prepare & update CSMS and SIKA document (if Necessary) | SH&E
- | Review and Update document, if necessary | SH&E
Records
- | Review, Screening & Filing Documents | SH&E
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE related) | SH&E
- | Review and Update PPE Stock and Control | SH&E
- | Update PPE Record | SH&E
- | Conduct of Work permit at warehouse, Lab & office (if Necessary) | Opr, Log, Lab
- | Conduct of Waste management, If necessary | Log, Opr, SH&E
Maintenance equipment:
- | Review Maintenance Schedule of Laboratory equipment | Lab
- | Review and Update Maintenance Schedule of Light Vehicle | Log, HR
10. Emergency Response Plan
- | Review and Update ERP Program | SH&E
- | Review and Update Emergency Response Team | SH&E
- | Conduct Drill at Office and Warehouse | All Dept
- | Review & evaluation of Emergency Drill | SH&E
- | Evaluation of Emergency Equipment | SH&E
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard | SH&E
11. Performance
- | Review and Record SH&E Performance every month | SH&E
- | Review and Update SH&E Monthly report | SH&E
- | Evaluation SH&E Performance | SH&E
- | Review and Update Leading & Lagging Indicator | SH&E
12. Monitoring Measurement & Evaluation
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature) | SH&E
- | Conduct Measurement of Industrial Hygiene | SH&E
- | Review and Update MCU Schedule | SH&E
- | Conduct MCU include audiometry, Alcohol & Drugs Test (as per schedule) | HR
- | Evaluation of MCU Result (as per schedule) | HR, SH&E
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action
- | Create the Investigation Team | SH&E
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur) | Related Dept
- | Review and update Incident and Accident Investigation Report (as per Incident occur) | SH&E
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur) | Related Dept
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur) | Related Dept
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur) | SH&E
- | Conduct Observation Card Program | All Dept
- | Record and evaluation observation card | SH&E
14. Inspection & Internal Audit
Inspection
- | Review and Update Inspection Schedule | SH&E
- | Conduct Inspection Vehicle for Subcon | Log
- | Conduct Operation Vehicle (Pre-Trip Inspection) | Log, HR
- | Conduct General Inspection at Office, Lab and Warehouse | SH&E
- | Conduct PPE Inspection | SH&E
Audit
- | Review and Update Schedule of Internal Audit Include Auditor Team | SH&E
- | Conduct Audit Internal | Related Dept
- | Review & Evaluation Internal Audit Result & Record it | SH&E
- | Conduct Audit Subcontractor | Proc, SH&E
15. Management Review
- | Review and Update Management Review Schedule | SH&E
- | Conduct Management Review | All Dept
- | Evaluation of Management Review Result | All Dept
- | Review and Evaluation HSE Activity Plan 2018 | SH&E
- | Conduct Corrective Action from Management Review Result (End of Year) | SH&E
| Total of Action Item Program (Jan) |  |  | 0
| Total of Compliance Action Item Program |  |  | #REF!
Jakarta, 29 January 2019
Prepared by
Leni Andani
SH&E Officer

## Mar
Element
Management Commitment
Resources Structure & Responsibility
Legal Business Compliance
Risk Management
Operational Control
SH&E Activity Plan 2020
Element |  | PIC | Y/N/N/A | Mar
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2018 & Golden Rules | SH&E, BOD
- | Review and Update SH&E Activity Plan | SH&E
- | SH&E Policy, Objectives & SH&E Activity Plan Socialization | SH&E
- | Management Walk Through | Log, Opr, SH&E, BOD |  | LM
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC | SH&E, Opr, Lab, Log
- | Review of Criteria Risk Assessment | SH&E
- | Evaluation Risk Assessment Compliance with Local Legal Regulation | SH&E
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary) | SH&E, Opr, Lab, Log
- | Review and Update MSDS | SH&E, Opr, Log
3. Management of Change
- | Conduct Management of Change | Opr, Log, Lab, SH&E
- | Review and Update Management of Change | Opr, Log, Lab, SH&E
- | Evaluation of MoC | Opr, Log, Lab, SH&E
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | SH&E, Legal
- | Evaluation of Compliance Local & International Legal Regulation | SH&E, Legal
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI | HR
- | Review and Update Structure Organization of SH&E | SH&E
- | Review and Update Organization SH&E Commite | SH&E
- | Update Jobdesc and Responsibility | HR
6. Training & Competency
- | Conduct SH&E Induction for new employee | SH&E
- | Update Training Schedule 2020 | HR
- | Update Training Matrix & Training Need Analysis 2020 | HR
7. Communications
- | Conduct SH&E Monthly Meeting | SH&E
- | Conduct SH&E Committee Meeting | SH&E
- | Review and Update OHS Sign or Label | SH&E
- | Conduct SH&E Toolbox Meeting | Opr, Log, Lab
- | Conduct Safety Talk (if necessary) | Opr, Log, Lab
- | Review and Revise SH&E Handbook | SH&E
- | Distribution & Socialization SH&E HandBook | SH&E
- | Updated SH&E Alert (Templated at HSE Board) | SH&E
- | Conduct SH&E Buletin and SH&E Campaign | SH&E
- | Conduct SH&E reward Program | SH&E
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update SH&E Policy, Procedure & Work Instruction | SH&E
- | Review and Update Internal document & external document | SH&E
- | Prepare & update CSMS and SIKA document (if Necessary) | SH&E
- | Review and Update document, if necessary | SH&E
Records
- | Review, Screening & Filing Documents | SH&E
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE related) | SH&E
- | Review and Update PPE Stock and Control | SH&E
- | Update PPE Record | SH&E
- | Conduct of Work permit at warehouse, Lab & office (if Necessary) | Opr, Log, Lab
- | Conduct of Waste management, If necessary | Log, Opr, SH&E
Maintenance equipment:
- | Review Maintenance Schedule of Laboratory equipment | Lab
- | Review and Update Maintenance Schedule of Light Vehicle | Log, HR
10. Emergency Response Plan
- | Review and Update ERP Program | SH&E
- | Review and Update Emergency Response Team | SH&E
- | Conduct Drill at Office and Warehouse | All Dept
- | Review & evaluation of Emergency Drill | SH&E
- | Evaluation of Emergency Equipment | SH&E
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard | SH&E
11. Performance
- | Review and Record SH&E Performance every month | SH&E
- | Review and Update SH&E Monthly report | SH&E
- | Evaluation SH&E Performance | SH&E
- | Review and Update Leading & Lagging Indicator | SH&E
12. Monitoring Measurement & Evaluation
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature) | SH&E
- | Conduct Measurement of Industrial Hygiene | SH&E
- | Review and Update MCU Schedule | SH&E
- | Conduct MCU include audiometry, Alcohol & Drugs Test (as per schedule) | HR
- | Evaluation of MCU Result (as per schedule) | HR, SH&E
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action
- | Create the Investigation Team | SH&E
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur) | Related Dept
- | Review and update Incident and Accident Investigation Report (as per Incident occur) | SH&E
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur) | Related Dept
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur) | Related Dept
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur) | SH&E
- | Conduct Observation Card Program | All Dept
- | Record and evaluation observation card | SH&E
14. Inspection & Internal Audit
Inspection
- | Review and Update Inspection Schedule | SH&E
- | Conduct Inspection Vehicle for Subcon | Log
- | Conduct Operation Vehicle (Pre-Trip Inspection) | Log, HR
- | Conduct General Inspection at Office, Lab and Warehouse | SH&E
- | Conduct PPE Inspection | SH&E
Audit
- | Review and Update Schedule of Internal Audit Include Auditor Team | SH&E
- | Conduct Audit Internal | Related Dept
- | Review & Evaluation Internal Audit Result & Record it | SH&E
- | Conduct Audit Subcontractor | Proc, SH&E
15. Management Review
- | Review and Update Management Review Schedule | SH&E
- | Conduct Management Review | All Dept
- | Evaluation of Management Review Result | All Dept
- | Review and Evaluation HSE Activity Plan 2018 | SH&E
- | Conduct Corrective Action from Management Review Result (End of Year) | SH&E
| Total of Action Item Program (Jan) |  |  | 0
| Total of Compliance Action Item Program |  |  | #REF!
Jakarta, 29 January 2019
Prepared by
Leni Andani
SH&E Officer

## Apr
Element
Management Commitment
Resources Structure & Responsibility
Legal Business Compliance
Risk Management
Operational Control
SH&E Activity Plan 2020
Element |  | PIC | Y/N/N/A | Apr
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2018 & Golden Rules | SH&E, BOD
- | Review and Update SH&E Activity Plan | SH&E
- | SH&E Policy, Objectives & SH&E Activity Plan Socialization | SH&E
- | Management Walk Through | Log, Opr, SH&E, BOD |  | SM
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC | SH&E, Opr, Lab, Log
- | Review of Criteria Risk Assessment | SH&E
- | Evaluation Risk Assessment Compliance with Local Legal Regulation | SH&E
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary) | SH&E, Opr, Lab, Log
- | Review and Update MSDS | SH&E, Opr, Log
3. Management of Change
- | Conduct Management of Change | Opr, Log, Lab, SH&E
- | Review and Update Management of Change | Opr, Log, Lab, SH&E
- | Evaluation of MoC | Opr, Log, Lab, SH&E
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | SH&E, Legal
- | Evaluation of Compliance Local & International Legal Regulation | SH&E, Legal
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI | HR
- | Review and Update Structure Organization of SH&E | SH&E
- | Review and Update Organization SH&E Commite | SH&E
- | Update Jobdesc and Responsibility | HR
6. Training & Competency
- | Conduct SH&E Induction for new employee | SH&E
- | Update Training Schedule 2020 | HR
- | Update Training Matrix & Training Need Analysis 2020 | HR
7. Communications
- | Conduct SH&E Monthly Meeting | SH&E
- | Conduct SH&E Committee Meeting | SH&E
- | Review and Update OHS Sign or Label | SH&E
- | Conduct SH&E Toolbox Meeting | Opr, Log, Lab
- | Conduct Safety Talk (if necessary) | Opr, Log, Lab
- | Review and Revise SH&E Handbook | SH&E
- | Distribution & Socialization SH&E HandBook | SH&E
- | Updated SH&E Alert (Templated at HSE Board) | SH&E
- | Conduct SH&E Buletin and SH&E Campaign | SH&E
- | Conduct SH&E reward Program | SH&E
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update SH&E Policy, Procedure & Work Instruction | SH&E
- | Review and Update Internal document & external document | SH&E
- | Prepare & update CSMS and SIKA document (if Necessary) | SH&E
- | Review and Update document, if necessary | SH&E
Records
- | Review, Screening & Filing Documents | SH&E
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE related) | SH&E
- | Review and Update PPE Stock and Control | SH&E
- | Update PPE Record | SH&E
- | Conduct of Work permit at warehouse, Lab & office (if Necessary) | Opr, Log, Lab
- | Conduct of Waste management, If necessary | Log, Opr, SH&E
Maintenance equipment:
- | Review Maintenance Schedule of Laboratory equipment | Lab
- | Review and Update Maintenance Schedule of Light Vehicle | Log, HR
10. Emergency Response Plan
- | Review and Update ERP Program | SH&E
- | Review and Update Emergency Response Team | SH&E
- | Conduct Drill at Office and Warehouse | All Dept
- | Review & evaluation of Emergency Drill | SH&E
- | Evaluation of Emergency Equipment | SH&E
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard | SH&E
11. Performance
- | Review and Record SH&E Performance every month | SH&E
- | Review and Update SH&E Monthly report | SH&E
- | Evaluation SH&E Performance | SH&E
- | Review and Update Leading & Lagging Indicator | SH&E
12. Monitoring Measurement & Evaluation
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature) | SH&E
- | Conduct Measurement of Industrial Hygiene | SH&E
- | Review and Update MCU Schedule | SH&E
- | Conduct MCU include audiometry, Alcohol & Drugs Test (as per schedule) | HR
- | Evaluation of MCU Result (as per schedule) | HR, SH&E
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action
- | Create the Investigation Team | SH&E
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur) | Related Dept
- | Review and update Incident and Accident Investigation Report (as per Incident occur) | SH&E
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur) | Related Dept
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur) | Related Dept
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur) | SH&E
- | Conduct Observation Card Program | All Dept
- | Record and evaluation observation card | SH&E
14. Inspection & Internal Audit
Inspection
- | Review and Update Inspection Schedule | SH&E
- | Conduct Inspection Vehicle for Subcon | Log
- | Conduct Operation Vehicle (Pre-Trip Inspection) | Log, HR
- | Conduct General Inspection at Office, Lab and Warehouse | SH&E
- | Conduct PPE Inspection | SH&E
Audit
- | Review and Update Schedule of Internal Audit Include Auditor Team | SH&E
- | Conduct Audit Internal | Related Dept
- | Review & Evaluation Internal Audit Result & Record it | SH&E
- | Conduct Audit Subcontractor | Proc, SH&E
15. Management Review
- | Review and Update Management Review Schedule | SH&E
- | Conduct Management Review | All Dept
- | Evaluation of Management Review Result | All Dept
- | Review and Evaluation HSE Activity Plan 2018 | SH&E
- | Conduct Corrective Action from Management Review Result (End of Year) | SH&E
| Total of Action Item Program (Jan) |  |  | 0
| Total of Compliance Action Item Program |  |  | #REF!
Jakarta, 29 January 2019
| Prepared by |  |  | Reviewed by
| Leni Andani |  |  | Yosep Dody
| SH&E Officer |  |  | SH&E Manager

## May
Element
Management Commitment
Resources Structure & Responsibility
Legal Business Compliance
Risk Management
Operational Control
SH&E Activity Plan 2020
Element |  | PIC | Y/N/N/A | May
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2018 & Golden Rules | SH&E, BOD
- | Review and Update SH&E Activity Plan | SH&E
- | SH&E Policy, Objectives & SH&E Activity Plan Socialization | SH&E
- | Management Walk Through | Log, Opr, SH&E, BOD |  | Dir
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC | SH&E, Opr, Lab, Log
- | Review of Criteria Risk Assessment | SH&E
- | Evaluation Risk Assessment Compliance with Local Legal Regulation | SH&E
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary) | SH&E, Opr, Lab, Log
- | Review and Update MSDS | SH&E, Opr, Log
3. Management of Change
- | Conduct Management of Change | Opr, Log, Lab, SH&E
- | Review and Update Management of Change | Opr, Log, Lab, SH&E
- | Evaluation of MoC | Opr, Log, Lab, SH&E
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | SH&E, Legal
- | Evaluation of Compliance Local & International Legal Regulation | SH&E, Legal
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI | HR
- | Review and Update Structure Organization of SH&E | SH&E
- | Review and Update Organization SH&E Commite | SH&E
- | Update Jobdesc and Responsibility | HR
6. Training & Competency
- | Conduct SH&E Induction for new employee | SH&E
- | Update Training Schedule 2020 | HR
- | Update Training Matrix & Training Need Analysis 2020 | HR
7. Communications
- | Conduct SH&E Monthly Meeting | SH&E
- | Conduct SH&E Committee Meeting | SH&E
- | Review and Update OHS Sign or Label | SH&E
- | Conduct SH&E Toolbox Meeting | Opr, Log, Lab
- | Conduct Safety Talk (if necessary) | Opr, Log, Lab
- | Review and Revise SH&E Handbook | SH&E
- | Distribution & Socialization SH&E HandBook | SH&E
- | Updated SH&E Alert (Templated at HSE Board) | SH&E
- | Conduct SH&E Buletin and SH&E Campaign | SH&E
- | Conduct SH&E reward Program | SH&E
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update SH&E Policy, Procedure & Work Instruction | SH&E
- | Review and Update Internal document & external document | SH&E
- | Prepare & update CSMS and SIKA document (if Necessary) | SH&E
- | Review and Update document, if necessary | SH&E
Records
- | Review, Screening & Filing Documents | SH&E
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE related) | SH&E
- | Review and Update PPE Stock and Control | SH&E
- | Update PPE Record | SH&E
- | Conduct of Work permit at warehouse, Lab & office (if Necessary) | Opr, Log, Lab
- | Conduct of Waste management, If necessary | Log, Opr, SH&E
Maintenance equipment:
- | Review Maintenance Schedule of Laboratory equipment | Log, HR
- | Review and Update Maintenance Schedule of Light Vehicle
10. Emergency Response Plan |  | SH&E
- | Review and Update ERP Program | SH&E
- | Review and Update Emergency Response Team | All Dept
- | Conduct Drill at Office and Warehouse | SH&E
- | Review & evaluation of Emergency Drill | SH&E
- | Evaluation of Emergency Equipment | SH&E
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard
11. Performance |  | SH&E
- | Review and Record SH&E Performance every month | SH&E
- | Review and Update SH&E Monthly report | SH&E
- | Evaluation SH&E Performance | SH&E
- | Review and Update Leading & Lagging Indicator
12. Monitoring Measurement & Evaluation |  | SH&E
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature) | SH&E
- | Conduct Measurement of Industrial Hygiene | SH&E
- | Review and Update MCU Schedule | HR
- | Conduct MCU include audiometry, Alcohol & Drugs Test (as per schedule) | HR, SH&E
- | Evaluation of MCU Result (as per schedule)
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action |  | SH&E
- | Create the Investigation Team | Related Dept
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur) | SH&E
- | Review and update Incident and Accident Investigation Report (as per Incident occur) | Related Dept
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur) | Related Dept
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur) | SH&E
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur) | All Dept
- | Conduct Observation Card Program | SH&E
- | Record and evaluation observation card
14. Inspection & Internal Audit
| Inspection | SH&E
- | Review and Update Inspection Schedule | Log
- | Conduct Inspection Vehicle for Subcon | Log, HR
- | Conduct Operation Vehicle (Pre-Trip Inspection) | SH&E
- | Conduct General Inspection at Office, Lab and Warehouse | SH&E
- | Conduct PPE Inspection
| Audit | SH&E
- | Review and Update Schedule of Internal Audit Include Auditor Team | Related Dept
- | Conduct Audit Internal | SH&E
- | Review & Evaluation Internal Audit Result & Record it | Proc, SH&E
- | Conduct Audit Subcontractor
15. Management Review |  | SH&E
- | Review and Update Management Review Schedule | All Dept
- | Conduct Management Review | All Dept
- | Evaluation of Management Review Result | SH&E
- | Review and Evaluation HSE Activity Plan 2018 | SH&E
- | Conduct Corrective Action from Management Review Result (End of Year)
| Total of Action Item Program (Jan) |  |  | 0
| Total of Compliance Action Item Program |  |  | #REF!
Jakarta, 29 January 2019
Prepared by
Leni Andani
SH&E Officer

## June
Element
Management Commitment
Resources Structure & Responsibility
Legal Business Compliance
Risk Management
Operational Control
SH&E Activity Plan 2020
Element |  | PIC | Y/N/N/A
June
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2020 & Golden Rules | SH&E, BOD
- | Review and Update SH&E Activity Plan | SH&E
- | SH&E Policy, Objectives & SH&E Activity Plan Socialization | SH&E
- | Management Walk Through | Log, Opr, SH&E, BOD |  | OM/MC
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC | SH&E, Opr, Lab, Log
- | Review of Criteria Risk Assessment | SH&E
- | Evaluation Risk Assessment Compliance with Local Legal Regulation | SH&E
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary) | SH&E, Opr, Lab, Log
- | Review and Update MSDS | SH&E, Opr, Log
3. Management of Change
- | Conduct Management of Change | Opr, Log, Lab, SH&E
- | Review and Update Management of Change | Opr, Log, Lab, SH&E
- | Evaluation of MoC | Opr, Log, Lab, SH&E
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | SH&E, Legal
- | Evaluation of Compliance Local & International Legal Regulation | SH&E, Legal
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI | HR
- | Review and Update Structure Organization of SH&E | SH&E
- | Review and Update Organization SH&E Commite | SH&E
- | Update Jobdesc and Responsibility | HR
6. Training & Competency
- | Conduct SH&E Induction for new employee | SH&E
- | Update Training Schedule 2019 | HR
- | Update Training Matrix & Training Need Analysis 2019 | HR
7. Communications
- | Conduct SH&E Monthly Meeting | SH&E
- | Conduct SH&E Committee Meeting | SH&E
- | Review and Update OHS Sign or Label | SH&E
- | Conduct SH&E Toolbox Meeting | Opr, Log, Lab
- | Conduct Safety Talk (if necessary) | Opr, Log, Lab
- | Review and Revise SH&E Handbook | SH&E
- | Distribution & Socialization SH&E HandBook | SH&E
- | Updated SH&E Alert (Templated at HSE Board) | SH&E
- | Conduct SH&E Buletin and SH&E Campaign | SH&E
- | Conduct SH&E reward Program | SH&E
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update SH&E Policy, Procedure & Work Instruction | SH&E
- | Review and Update Internal document & external document | SH&E
- | Prepare & update CSMS and SIKA document (if Necessary) | SH&E
- | Review and Update document, if necessary | SH&E
Records
- | Review, Screening & Filing Documents | SH&E
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE related) | SH&E
- | Review and Update PPE Stock and Control | SH&E
- | Update PPE Record | SH&E
- | Conduct of Work permit at warehouse, Lab & office (if Necessary) | Opr, Log, Lab
- | Conduct of Waste management, If necessary | Log, Opr, SH&E
Maintenance equipment:
- | Review Maintenance Schedule of Laboratory equipment | Lab
- | Review and Update Maintenance Schedule of Light Vehicle | HR, Log
10. Emergency Response Plan
- | Review and Update ERP Program | SH&E
- | Review and Update Emergency Response Team | All Dept
- | Conduct Drill at Office and Warehouse | SH&E
- | Review & evaluation of Emergency Drill | SH&E
- | Evaluation of Emergency Equipment | SH&E
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard
11. Performance |  | SH&E
- | Review and Record SH&E Performance every month | SH&E
- | Review and Update SH&E Monthly report | SH&E
- | Evaluation SH&E Performance | SH&E
- | Review and Update Leading & Lagging Indicator
12. Monitoring Measurement & Evaluation |  | SH&E
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature) | SH&E
- | Conduct Measurement of Industrial Hygiene | SH&E
- | Review and Update MCU Schedule | HR
- | Conduct MCU include audiometry, Alcohol & Drugs Test (as per schedule) | HR, SH&E
- | Evaluation of MCU Result (as per schedule)
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action |  | SH&E
- | Create the Investigation Team | Related Dept
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur) | SH&E
- | Review and update Incident and Accident Investigation Report (as per Incident occur) | Related Dept
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur) | Related Dept
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur) | SH&E
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur) | All Dept
- | Conduct Observation Card Program | SH&E
- | Record and evaluation observation card
14. Inspection & Internal Audit
| Inspection | SH&E
- | Review and Update Inspection Schedule | Log
- | Conduct Inspection Vehicle for Subcon | Log, HR
- | Conduct Operation Vehicle (Pre-Trip Inspection) | SH&E
- | Conduct General Inspection at Office, Lab and Warehouse | SH&E
- | Conduct PPE Inspection
| Audit | SH&E
- | Review and Update Schedule of Internal Audit Include Auditor Team | Related Dept
- | Conduct Audit Internal | SH&E
- | Review & Evaluation Internal Audit Result & Record it | Proc, SH&E
- | Conduct Audit Subcontractor
15. Management Review |  | SH&E
- | Review and Update Management Review Schedule | All Dept
- | Conduct Management Review | All Dept
- | Evaluation of Management Review Result | SH&E
- | Review and Evaluation HSE Activity Plan 2018 | SH&E
- | Conduct Corrective Action from Management Review Result (End of Year)
| Total of Action Item Program (Jan) |  |  | 0
| Total of Compliance Action Item Program |  |  | #REF!
Jakarta, 29 January 2019
Prepared by
Leni Andani
SH&E Officer

## Jul
Element
Management Commitment
Resources Structure & Responsibility
Legal Business Compliance
Risk Management
Operational Control
SH&E Activity Plan 2020
Element |  | PIC | Y/N/N/A
July
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2018 & Golden Rules | SH&E, BOD
- | Review and Update SH&E Activity Plan | SH&E
- | SH&E Policy, Objectives & SH&E Activity Plan Socialization | SH&E
- | Management Walk Through | Log, Opr, SH&E, BOD |  | Dir Ops
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC | SH&E, Opr, Lab, Log
- | Review of Criteria Risk Assessment | SH&E
- | Evaluation Risk Assessment Compliance with Local Legal Regulation | SH&E
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary) | SH&E, Opr, Lab, Log
- | Review and Update MSDS | SH&E, Opr, Log
3. Management of Change
- | Conduct Management of Change | Opr, Log, Lab, SH&E
- | Review and Update Management of Change | Opr, Log, Lab, SH&E
- | Evaluation of MoC | Opr, Log, Lab, SH&E
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | SH&E, Legal
- | Evaluation of Compliance Local & International Legal Regulation | SH&E, Legal
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI | HR
- | Review and Update Structure Organization of SH&E | SH&E
- | Review and Update Organization SH&E Commite | SH&E
- | Update Jobdesc and Responsibility | HR
6. Training & Competency
- | Conduct SH&E Induction for new employee | SH&E
- | Update Training Schedule 2020 | HR
- | Update Training Matrix & Training Need Analysis 2020 | HR
7. Communications
- | Conduct SH&E Monthly Meeting | SH&E
- | Conduct SH&E Committee Meeting | SH&E
- | Review and Update OHS Sign or Label | SH&E
- | Conduct SH&E Toolbox Meeting | Opr, Log, Lab
- | Conduct Safety Talk (if necessary) | Opr, Log, Lab
- | Review and Revise SH&E Handbook | SH&E
- | Distribution & Socialization SH&E HandBook | SH&E
- | Updated SH&E Alert (Templated at HSE Board) | SH&E
- | Conduct SH&E Buletin and SH&E Campaign | SH&E
- | Conduct SH&E reward Program | SH&E
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update SH&E Policy, Procedure & Work Instruction | SH&E
- | Review and Update Internal document & external document | SH&E
- | Prepare & update CSMS and SIKA document (if Necessary) | SH&E
- | Review and Update document, if necessary | SH&E
Records
- | Review, Screening & Filing Documents | SH&E
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE related) | SH&E
- | Review and Update PPE Stock and Control | SH&E
- | Update PPE Record | SH&E
- | Conduct of Work permit at warehouse, Lab & office (if Necessary) | Opr, Log, Lab
- | Conduct of Waste management, If necessary | Log, Opr, SH&E
Maintenance equipment:
- | Review Maintenance Schedule of Laboratory equipment | Lab
- | Review and Update Maintenance Schedule of Light Vehicle | SH&E
10. Emergency Response Plan
- | Review and Update ERP Program | SH&E
- | Review and Update Emergency Response Team | All Dept
- | Conduct Drill at Office and Warehouse | SH&E
- | Review & evaluation of Emergency Drill | SH&E
- | Evaluation of Emergency Equipment | SH&E
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard | SH&E
11. Performance |  | SH&E
- | Review and Record SH&E Performance every month | SH&E
- | Review and Update SH&E Monthly report | SH&E
- | Evaluation SH&E Performance | SH&E
- | Review and Update Leading & Lagging Indicator
12. Monitoring Measurement & Evaluation |  | SH&E
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature) | SH&E
- | Conduct Measurement of Industrial Hygiene | SH&E
- | Review and Update MCU Schedule | HR
- | Conduct MCU include audiometry, Alcohol & Drugs Test (as per schedule) | HR, SH&E
- | Evaluation of MCU Result (as per schedule)
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action |  | SH&E
- | Create the Investigation Team | Related Dept
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur) | SH&E
- | Review and update Incident and Accident Investigation Report (as per Incident occur) | Related Dept
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur) | Related Dept
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur) | SH&E
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur) | All Dept
- | Conduct Observation Card Program | SH&E
- | Record and evaluation observation card
14. Inspection & Internal Audit
| Inspection | SH&E
- | Review and Update Inspection Schedule | Log
- | Conduct Inspection Vehicle for Subcon | Log, HR
- | Conduct Operation Vehicle (Pre-Trip Inspection) | SH&E
- | Conduct General Inspection at Office, Lab and Warehouse | SH&E
- | Conduct PPE Inspection | SH&E
Audit
- | Review and Update Schedule of Internal Audit Include Auditor Team | SH&E
- | Conduct Audit Internal | Related Dept
- | Review & Evaluation Internal Audit Result & Record it | SH&E
- | Conduct Audit Subcontractor | Proc, SH&E
15. Management Review
- | Review and Update Management Review Schedule | SH&E
- | Conduct Management Review | All Dept
- | Evaluation of Management Review Result | All Dept
- | Review and Evaluation HSE Activity Plan 2018 | SH&E
- | Conduct Corrective Action from Management Review Result (End of Year) | SH&E
| Total of Action Item Program (Jan) |  |  | 0
| Total of Compliance Action Item Program |  |  | #REF!
Jakarta, 29 January 2019
Prepared by
Leni Andani
SH&E Officer

## Aug
Element
Management Commitment
Resources Structure & Responsibility
Legal Business Compliance
Risk Management
Operational Control
SH&E Activity Plan 2020
Element |  | PIC | Y/N/N/A
Aug
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2018 & Golden Rules | SH&E, BOD
- | Review and Update SH&E Activity Plan | SH&E
- | SH&E Policy, Objectives & SH&E Activity Plan Socialization | SH&E
- | Management Walk Through | Log, Opr, SH&E, BOD |  | LM
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC | SH&E, Opr, Lab, Log
- | Review of Criteria Risk Assessment | SH&E
- | Evaluation Risk Assessment Compliance with Local Legal Regulation | SH&E
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary) | SH&E, Opr, Lab, Log
- | Review and Update MSDS | SH&E, Opr, Log
3. Management of Change
- | Conduct Management of Change | Opr, Log, Lab, SH&E
- | Review and Update Management of Change | Opr, Log, Lab, SH&E
- | Evaluation of MoC | Opr, Log, Lab, SH&E
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | SH&E, Legal
- | Evaluation of Compliance Local & International Legal Regulation | SH&E, Legal
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI | HR
- | Review and Update Structure Organization of SH&E | SH&E
- | Review and Update Organization SH&E Commite | SH&E
- | Update Jobdesc and Responsibility | HR
6. Training & Competency
- | Conduct SH&E Induction for new employee | SH&E
- | Update Training Schedule 2020 | HR
- | Update Training Matrix & Training Need Analysis 2020 | HR
7. Communications
- | Conduct SH&E Monthly Meeting | SH&E
- | Conduct SH&E Committee Meeting | SH&E
- | Review and Update OHS Sign or Label | SH&E
- | Conduct SH&E Toolbox Meeting | Opr, Log, Lab
- | Conduct Safety Talk (if necessary) | Opr, Log, Lab
- | Review and Revise SH&E Handbook | SH&E
- | Distribution & Socialization SH&E HandBook | SH&E
- | Updated SH&E Alert (Templated at HSE Board) | SH&E
- | Conduct SH&E Buletin and SH&E Campaign | SH&E
- | Conduct SH&E reward Program | SH&E
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update SH&E Policy, Procedure & Work Instruction | SH&E
- | Review and Update Internal document & external document | SH&E
- | Prepare & update CSMS and SIKA document (if Necessary) | SH&E
- | Review and Update document, if necessary | SH&E
Records
- | Review, Screening & Filing Documents | SH&E
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE related) | SH&E
- | Review and Update PPE Stock and Control | SH&E
- | Update PPE Record | SH&E
- | Conduct of Work permit at warehouse, Lab & office (if Necessary) | Opr, Log, Lab
- | Conduct of Waste management, If necessary | Log, Opr, SH&E
Maintenance equipment:
- | Review Maintenance Schedule of Laboratory equipment | Lab
- | Review and Update Maintenance Schedule of Light Vehicle | HR, Log
10. Emergency Response Plan
- | Review and Update ERP Program | SH&E
- | Review and Update Emergency Response Team | All Dept
- | Conduct Drill at Office and Warehouse | SH&E
- | Review & evaluation of Emergency Drill | SH&E
- | Evaluation of Emergency Equipment | SH&E
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard | SH&E
11. Performance
- | Review and Record SH&E Performance every month | SH&E
- | Review and Update SH&E Monthly report | SH&E
- | Evaluation SH&E Performance | SH&E
- | Review and Update Leading & Lagging Indicator | SH&E
12. Monitoring Measurement & Evaluation |  | SH&E
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature) | SH&E
- | Conduct Measurement of Industrial Hygiene | HR
- | Review and Update MCU Schedule | HR, SH&E
- | Conduct MCU include audiometry, Alcohol & Drugs Test (as per schedule)
- | Evaluation of MCU Result (as per schedule) | SH&E
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action
- | Create the Investigation Team | Related Dept
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur) | SH&E
- | Review and update Incident and Accident Investigation Report (as per Incident occur) | Related Dept
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur) | Related Dept
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur) | SH&E
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur) | All Dept
- | Conduct Observation Card Program | SH&E
- | Record and evaluation observation card
14. Inspection & Internal Audit
| Inspection | SH&E
- | Review and Update Inspection Schedule | Log
- | Conduct Inspection Vehicle for Subcon | Log, HR
- | Conduct Operation Vehicle (Pre-Trip Inspection) | SH&E
- | Conduct General Inspection at Office, Lab and Warehouse | SH&E
- | Conduct PPE Inspection | SH&E
Audit
- | Review and Update Schedule of Internal Audit Include Auditor Team | SH&E
- | Conduct Audit Internal | Related Dept
- | Review & Evaluation Internal Audit Result & Record it | SH&E
- | Conduct Audit Subcontractor | Proc, SH&E
15. Management Review
- | Review and Update Management Review Schedule | SH&E
- | Conduct Management Review | All Dept
- | Evaluation of Management Review Result | All Dept
- | Review and Evaluation HSE Activity Plan 2018 | SH&E
- | Conduct Corrective Action from Management Review Result (End of Year) | SH&E
| Total of Action Item Program (Jan) |  |  | 0
| Total of Compliance Action Item Program |  |  | #REF!
Jakarta, 29 January 2019
Prepared by
Leni Andani
SH&E Officer

## Sept
Element
Management Commitment
Resources Structure & Responsibility
Legal Business Compliance
Risk Management
Operational Control
SH&E Activity Plan 2020
Element |  | PIC | Y/N/N/A
Sept
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2020 & Golden Rules | SH&E, BOD
- | Review and Update SH&E Activity Plan | SH&E
- | SH&E Policy, Objectives & SH&E Activity Plan Socialization | SH&E
- | Management Walk Through | Log, Opr, SH&E, BOD |  | SM
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC | SH&E, Opr, Lab, Log
- | Review of Criteria Risk Assessment | SH&E
- | Evaluation Risk Assessment Compliance with Local Legal Regulation | SH&E
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary) | SH&E, Opr, Lab, Log
- | Review and Update MSDS | SH&E, Opr, Log
3. Management of Change
- | Conduct Management of Change | Opr, Log, Lab, SH&E
- | Review and Update Management of Change | Opr, Log, Lab, SH&E
- | Evaluation of MoC | Opr, Log, Lab, SH&E
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | SH&E, Legal
- | Evaluation of Compliance Local & International Legal Regulation | SH&E, Legal
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI | HR
- | Review and Update Structure Organization of SH&E | SH&E
- | Review and Update Organization SH&E Commite | SH&E
- | Update Jobdesc and Responsibility | HR
6. Training & Competency
- | Conduct SH&E Induction for new employee | SH&E
- | Update Training Schedule 2019 | HR
- | Update Training Matrix & Training Need Analysis 2019 | HR
7. Communications
- | Conduct SH&E Monthly Meeting | SH&E
- | Conduct SH&E Committee Meeting | SH&E
- | Review and Update OHS Sign or Label | SH&E
- | Conduct SH&E Toolbox Meeting | Opr, Log, Lab
- | Conduct Safety Talk (if necessary) | Opr, Log, Lab
- | Review and Revise SH&E Handbook | SH&E
- | Distribution & Socialization SH&E HandBook | SH&E
- | Updated SH&E Alert (Templated at HSE Board) | SH&E
- | Conduct SH&E Buletin and SH&E Campaign | SH&E
- | Conduct SH&E reward Program | SH&E
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update SH&E Policy, Procedure & Work Instruction | SH&E
- | Review and Update Internal document & external document | SH&E
- | Prepare & update CSMS and SIKA document (if Necessary) | SH&E
- | Review and Update document, if necessary | SH&E
Records
- | Review, Screening & Filing Documents | SH&E
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE related) | SH&E
- | Review and Update PPE Stock and Control | SH&E
- | Update PPE Record | SH&E
- | Conduct of Work permit at warehouse, Lab & office (if Necessary) | Opr, Log, Lab
- | Conduct of Waste management, If necessary | Log, Opr, SH&E
Maintenance equipment:
- | Review Maintenance Schedule of Laboratory equipment | Lab
- | Review and Update Maintenance Schedule of Light Vehicle | HR, Log
10. Emergency Response Plan
- | Review and Update ERP Program | SH&E
- | Review and Update Emergency Response Team | All Dept
- | Conduct Drill at Office and Warehouse | SH&E
- | Review & evaluation of Emergency Drill | SH&E
- | Evaluation of Emergency Equipment | SH&E
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard | SH&E
11. Performance
- | Review and Record SH&E Performance every month | SH&E
- | Review and Update SH&E Monthly report | SH&E
- | Evaluation SH&E Performance | SH&E
- | Review and Update Leading & Lagging Indicator | SH&E
12. Monitoring Measurement & Evaluation
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature) | SH&E
- | Conduct Measurement of Industrial Hygiene | HR
- | Review and Update MCU Schedule | HR
- | Conduct MCU include audiometry, Alcohol & Drugs Test (as per schedule) | HR
- | Evaluation of MCU Result (as per schedule) | HR, SH&E
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action
- | Create the Investigation Team | SH&E
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur) | Related Dept
- | Review and update Incident and Accident Investigation Report (as per Incident occur) | Related Dept
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur) | SH&E
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur) | Related Dept
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur) | SH&E
- | Conduct Observation Card Program | All Dept
- | Record and evaluation observation card | SH&E
14. Inspection & Internal Audit
Inspection
- | Review and Update Inspection Schedule | SH&E
- | Conduct Inspection Vehicle for Subcon | Log
- | Conduct Operation Vehicle (Pre-Trip Inspection) | Log, HR
- | Conduct General Inspection at Office, Lab and Warehouse | SH&E
- | Conduct PPE Inspection | SH&E
Audit
- | Review and Update Schedule of Internal Audit Include Auditor Team | SH&E
- | Conduct Audit Internal | Related Dept
- | Review & Evaluation Internal Audit Result & Record it | SH&E
- | Conduct Audit Subcontractor | Proc, SH&E
15. Management Review
- | Review and Update Management Review Schedule | SH&E
- | Conduct Management Review | All Dept
- | Evaluation of Management Review Result | All Dept
- | Review and Evaluation HSE Activity Plan 2018 | SH&E
- | Conduct Corrective Action from Management Review Result (End of Year) | SH&E
| Total of Action Item Program (Jan) |  |  | 0
| Total of Compliance Action Item Program |  |  | #REF!
Jakarta, 29 January 2019
Prepared by
Leni Andani
SH&E Officer

## Oct
Element
Management Commitment
Resources Structure & Responsibility
Legal Business Compliance
Risk Management
Operational Control
SH&E Activity Plan 2020
Element |  | PIC | Y/N/N/A
Oct
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2018 & Golden Rules | SH&E, BOD
- | Review and Update SH&E Activity Plan | SH&E
- | SH&E Policy, Objectives & SH&E Activity Plan Socialization | SH&E
- | Management Walk Through | Log, Opr, SH&E, BOD |  | Dir
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC | SH&E, Opr, Lab, Log
- | Review of Criteria Risk Assessment | SH&E
- | Evaluation Risk Assessment Compliance with Local Legal Regulation | SH&E
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary) | SH&E, Opr, Lab, Log
- | Review and Update MSDS | SH&E, Opr, Log
3. Management of Change
- | Conduct Management of Change | Opr, Log, Lab, SH&E
- | Review and Update Management of Change | Opr, Log, Lab, SH&E
- | Evaluation of MoC | Opr, Log, Lab, SH&E
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | SH&E, Legal
- | Evaluation of Compliance Local & International Legal Regulation | SH&E, Legal
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI | HR
- | Review and Update Structure Organization of SH&E | SH&E
- | Review and Update Organization SH&E Commite | SH&E
- | Update Jobdesc and Responsibility | HR
6. Training & Competency
- | Conduct SH&E Induction for new employee | SH&E
- | Update Training Schedule 2020 | HR
- | Update Training Matrix & Training Need Analysis 2020 | HR
7. Communications
- | Conduct SH&E Monthly Meeting | SH&E
- | Conduct SH&E Committee Meeting | SH&E
- | Review and Update OHS Sign or Label | SH&E
- | Conduct SH&E Toolbox Meeting | Opr, Log, Lab
- | Conduct Safety Talk (if necessary) | Opr, Log, Lab
- | Review and Revise SH&E Handbook | SH&E
- | Distribution & Socialization SH&E HandBook | SH&E
- | Updated SH&E Alert (Templated at HSE Board) | SH&E
- | Conduct SH&E Buletin and SH&E Campaign | SH&E
- | Conduct SH&E reward Program | SH&E
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update SH&E Policy, Procedure & Work Instruction | SH&E
- | Review and Update Internal document & external document | SH&E
- | Prepare & update CSMS and SIKA document (if Necessary) | SH&E
- | Review and Update document, if necessary | SH&E
Records
- | Review, Screening & Filing Documents | SH&E
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE related) | SH&E
- | Review and Update PPE Stock and Control | SH&E
- | Update PPE Record | SH&E
- | Conduct of Work permit at warehouse, Lab & office (if Necessary) | Opr, Log, Lab
- | Conduct of Waste management, If necessary | Log, Opr, SH&E
Maintenance equipment:
- | Review Maintenance Schedule of Laboratory equipment | Lab
- | Review and Update Maintenance Schedule of Light Vehicle | HR, Log
10. Emergency Response Plan
- | Review and Update ERP Program | SH&E
- | Review and Update Emergency Response Team | All Dept
- | Conduct Drill at Office and Warehouse | SH&E
- | Review & evaluation of Emergency Drill | SH&E
- | Evaluation of Emergency Equipment | SH&E
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard | SH&E
11. Performance
- | Review and Record SH&E Performance every month | SH&E
- | Review and Update SH&E Monthly report | SH&E
- | Evaluation SH&E Performance | SH&E
- | Review and Update Leading & Lagging Indicator | SH&E
12. Monitoring Measurement & Evaluation
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature) | SH&E
- | Conduct Measurement of Industrial Hygiene | HR
- | Review and Update MCU Schedule | HR
- | Conduct MCU include audiometry, Alcohol & Drugs Test (as per schedule) | HR
- | Evaluation of MCU Result (as per schedule) | HR, SH&E
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action
- | Create the Investigation Team | SH&E
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur) | Related Dept
- | Review and update Incident and Accident Investigation Report (as per Incident occur) | Related Dept
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur) | SH&E
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur) | Related Dept
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur) | SH&E
- | Conduct Observation Card Program | All Dept
- | Record and evaluation observation card | SH&E
14. Inspection & Internal Audit
Inspection
- | Review and Update Inspection Schedule | SH&E
- | Conduct Inspection Vehicle for Subcon | Log
- | Conduct Operation Vehicle (Pre-Trip Inspection) | Log, HR
- | Conduct General Inspection at Office, Lab and Warehouse | SH&E
- | Conduct PPE Inspection | SH&E
Audit
- | Review and Update Schedule of Internal Audit Include Auditor Team | SH&E
- | Conduct Audit Internal | Related Dept
- | Review & Evaluation Internal Audit Result & Record it | SH&E
- | Conduct Audit Subcontractor | Proc, SH&E
15. Management Review
- | Review and Update Management Review Schedule | SH&E
- | Conduct Management Review | All Dept
- | Evaluation of Management Review Result | All Dept
- | Review and Evaluation HSE Activity Plan 2019 | SH&E
- | Conduct Corrective Action from Management Review Result (End of Year) | SH&E
| Total of Action Item Program (Jan) |  |  | 0
| Total of Compliance Action Item Program |  |  | #REF!
Jakarta, 29 January 2019
Prepared by
Leni Andani
SH&E Officer

## Nov
Element
Management Commitment
Resources Structure & Responsibility
Legal Business Compliance
Risk Management
Operational Control
SH&E Activity Plan 2019
Element |  | PIC | Y/N/N/A
Nov
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2018 & Golden Rules | SH&E, BOD
- | Review and Update SH&E Activity Plan | SH&E
- | SH&E Policy, Objectives & SH&E Activity Plan Socialization | SH&E
- | Management Walk Through | Log, Opr, SH&E, BOD |  | OM/MC
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC | SH&E, Opr, Lab, Log
- | Review of Criteria Risk Assessment | SH&E
- | Evaluation Risk Assessment Compliance with Local Legal Regulation | SH&E
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary) | SH&E, Opr, Lab, Log
- | Review and Update MSDS | SH&E, Opr, Log
3. Management of Change
- | Conduct Management of Change | Opr, Log, Lab, SH&E
- | Review and Update Management of Change | Opr, Log, Lab, SH&E
- | Evaluation of MoC | Opr, Log, Lab, SH&E
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | SH&E, Legal
- | Evaluation of Compliance Local & International Legal Regulation | SH&E, Legal
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI | HR
- | Review and Update Structure Organization of SH&E | SH&E
- | Review and Update Organization SH&E Commite | SH&E
- | Update Jobdesc and Responsibility | HR
6. Training & Competency
- | Conduct SH&E Induction for new employee | SH&E
- | Update Training Schedule 2020 | HR
- | Update Training Matrix & Training Need Analysis 2020 | HR
7. Communications
- | Conduct SH&E Monthly Meeting | SH&E
- | Conduct SH&E Committee Meeting | SH&E
- | Review and Update OHS Sign or Label | SH&E
- | Conduct SH&E Toolbox Meeting | Opr, Log, Lab
- | Conduct Safety Talk (if necessary) | Opr, Log, Lab
- | Review and Revise SH&E Handbook | SH&E
- | Distribution & Socialization SH&E HandBook | SH&E
- | Updated SH&E Alert (Templated at HSE Board) | SH&E
- | Conduct SH&E Buletin and SH&E Campaign | SH&E
- | Conduct SH&E reward Program | SH&E
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update SH&E Policy, Procedure & Work Instruction | SH&E
- | Review and Update Internal document & external document | SH&E
- | Prepare & update CSMS and SIKA document (if Necessary) | SH&E
- | Review and Update document, if necessary | SH&E
Records
- | Review, Screening & Filing Documents | SH&E
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE related) | SH&E
- | Review and Update PPE Stock and Control | SH&E
- | Update PPE Record | SH&E
- | Conduct of Work permit at warehouse, Lab & office (if Necessary) | Opr, Log, Lab
- | Conduct of Waste management, If necessary | Log, Opr, SH&E
Maintenance equipment:
- | Review Maintenance Schedule of Laboratory equipment | Lab
- | Review and Update Maintenance Schedule of Light Vehicle | HR, Log
10. Emergency Response Plan
- | Review and Update ERP Program | SH&E
- | Review and Update Emergency Response Team | All Dept
- | Conduct Drill at Office and Warehouse | SH&E
- | Review & evaluation of Emergency Drill | SH&E
- | Evaluation of Emergency Equipment | SH&E
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard | SH&E
11. Performance
- | Review and Record SH&E Performance every month | SH&E
- | Review and Update SH&E Monthly report | SH&E
- | Evaluation SH&E Performance | SH&E
- | Review and Update Leading & Lagging Indicator | SH&E
12. Monitoring Measurement & Evaluation
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature) | SH&E
- | Conduct Measurement of Industrial Hygiene | HR
- | Review and Update MCU Schedule | HR
- | Conduct MCU include audiometry, Alcohol & Drugs Test (as per schedule) | HR
- | Evaluation of MCU Result (as per schedule) | HR, SH&E
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action
- | Create the Investigation Team | SH&E
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur) | Related Dept
- | Review and update Incident and Accident Investigation Report (as per Incident occur) | Related Dept
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur) | SH&E
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur) | Related Dept
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur) | SH&E
- | Conduct Observation Card Program | All Dept
- | Record and evaluation observation card | SH&E
14. Inspection & Internal Audit
Inspection
- | Review and Update Inspection Schedule | SH&E
- | Conduct Inspection Vehicle for Subcon | Log
- | Conduct Operation Vehicle (Pre-Trip Inspection) | Log, HR
- | Conduct General Inspection at Office, Lab and Warehouse | SH&E
- | Conduct PPE Inspection | SH&E
Audit
- | Review and Update Schedule of Internal Audit Include Auditor Team | SH&E
- | Conduct Audit Internal | Related Dept
- | Review & Evaluation Internal Audit Result & Record it | SH&E
- | Conduct Audit Subcontractor | Proc, SH&E
15. Management Review
- | Review and Update Management Review Schedule | SH&E
- | Conduct Management Review | All Dept
- | Evaluation of Management Review Result | All Dept
- | Review and Evaluation HSE Activity Plan 2018 | SH&E
- | Conduct Corrective Action from Management Review Result (End of Year) | SH&E
| Total of Action Item Program (Jan) |  |  | 0
| Total of Compliance Action Item Program |  |  | #REF!
Jakarta, 29 January 2019
| Prepared by |  |  | Approved by
| Leni Andani |  |  | Junius Natalim
| SH&E Officer |  |  | Director

## Dec
Element
Management Commitment
Resources Structure & Responsibility
Legal Business Compliance
Risk Management
Operational Control
SH&E Activity Plan 2019
Element |  | PIC | Y/N/N/A
Dec
1. Management Commitment
- | Review and Update SH&E Policy, Objective 2018 & Golden Rules | SH&E, BOD
- | Review and Update SH&E Activity Plan | SH&E
- | SH&E Policy, Objectives & SH&E Activity Plan Socialization | SH&E
- | Management Walk Through | Log, Opr, SH&E, BOD |  | Dir Ops
2. Hazard Identification & Risk Assessments
- | Review and Update HIRADC | SH&E, Opr, Lab, Log
- | Review of Criteria Risk Assessment | SH&E
- | Evaluation Risk Assessment Compliance with Local Legal Regulation | SH&E
- | review and Update JSA at Field, Warehouse, Lab & Office (if Necessary) | SH&E, Opr, Lab, Log
- | Review and Update MSDS | SH&E, Opr, Log
3. Management of Change
- | Conduct Management of Change | Opr, Log, Lab, SH&E
- | Review and Update Management of Change | Opr, Log, Lab, SH&E
- | Evaluation of MoC | Opr, Log, Lab, SH&E
4. Legal Business Compliance
- | Review and Update Register Local & International Legal Regulation | SH&E, Legal
- | Evaluation of Compliance Local & International Legal Regulation | SH&E, Legal
5. Resources Structure & Responsibility
- | Review and Update Structure Organization Chart PT PHI | HR
- | Review and Update Structure Organization of SH&E | SH&E
- | Review and Update Organization SH&E Commite | SH&E
- | Update Jobdesc and Responsibility | HR
6. Training & Competency
- | Conduct SH&E Induction for new employee | SH&E
- | Update Training Schedule 2019 | HR
- | Update Training Matrix & Training Need Analysis 2019 | HR
7. Communications
- | Conduct SH&E Monthly Meeting | SH&E
- | Conduct SH&E Committee Meeting | SH&E
- | Review and Update OHS Sign or Label | SH&E
- | Conduct SH&E Toolbox Meeting | Opr, Log, Lab
- | Conduct Safety Talk (if necessary) | Opr, Log, Lab
- | Review and Revise SH&E Handbook | SH&E
- | Distribution & Socialization SH&E HandBook | SH&E
- | Updated SH&E Alert (Templated at HSE Board) | SH&E
- | Conduct SH&E Buletin and SH&E Campaign | SH&E
- | Conduct SH&E reward Program | SH&E
8. Documentation, Control of Document & Records
Documentation & Control
- | Review and Update SH&E Policy, Procedure & Work Instruction | SH&E
- | Review and Update Internal document & external document | SH&E
- | Prepare & update CSMS and SIKA document (if Necessary) | SH&E
- | Review and Update document, if necessary | SH&E
Records
- | Review, Screening & Filing Documents | SH&E
9. Operational Control
Record and Monitoring
- | Review and Update Jobs Matrix (Worker and PPE related) | SH&E
- | Review and Update PPE Stock and Control | SH&E
- | Update PPE Record | SH&E
- | Conduct of Work permit at warehouse, Lab & office (if Necessary) | Opr, Log, Lab
- | Conduct of Waste management, If necessary | Log, Opr, SH&E
Maintenance equipment:
- | Review Maintenance Schedule of Laboratory equipment | Lab
- | Review and Update Maintenance Schedule of Light Vehicle | HR, Log
10. Emergency Response Plan
- | Review and Update ERP Program | SH&E
- | Review and Update Emergency Response Team | All Dept
- | Conduct Drill at Office and Warehouse | SH&E
- | Review & evaluation of Emergency Drill | SH&E
- | Evaluation of Emergency Equipment | SH&E
- | Inspection Emergency Equipment at Office, Lab, Warehouse & Yard | SH&E
11. Performance
- | Review and Record SH&E Performance every month | SH&E
- | Review and Update SH&E Monthly report | SH&E
- | Evaluation SH&E Performance | SH&E
- | Review and Update Leading & Lagging Indicator | SH&E
12. Monitoring Measurement & Evaluation
- | Review and Update Schedule of Industrial Hygiene Program (Noise, Lighting, Humidity, Temperature) | SH&E
- | Conduct Measurement of Industrial Hygiene | HR
- | Review and Update MCU Schedule | HR
- | Conduct MCU include audiometry, Alcohol & Drugs Test (as per schedule) | HR
- | Evaluation of MCU Result (as per schedule) | HR, SH&E
13. Incident / Accident Investigation , Nonconformity, Corrective Action & Preventive Action
- | Create the Investigation Team | SH&E
- | Conduct Incident and Accident Investigation Report and record it (as per Incident occur) | Related Dept
- | Review and update Incident and Accident Investigation Report (as per Incident occur) | Related Dept
- | Evaluation of Incident/Accident for Corrective Action (as per Incident occur) | SH&E
- | Identification Nonconformity & Record of Corrective Action Result (as per Incident occur) | Related Dept
- | Conduct Lesson and Learn or Stand Down Meeting (as per Incident occur) | SH&E
- | Conduct Observation Card Program | All Dept
- | Record and evaluation observation card | SH&E
14. Inspection & Internal Audit
Inspection
- | Review and Update Inspection Schedule | SH&E
- | Conduct Inspection Vehicle for Subcon | Log
- | Conduct Operation Vehicle (Pre-Trip Inspection) | Log, HR
- | Conduct General Inspection at Office, Lab and Warehouse | SH&E
- | Conduct PPE Inspection | SH&E
Audit
- | Review and Update Schedule of Internal Audit Include Auditor Team | SH&E
- | Conduct Audit Internal | Related Dept
- | Review & Evaluation Internal Audit Result & Record it | SH&E
- | Conduct Audit Subcontractor | Proc, SH&E
15. Management Review
- | Review and Update Management Review Schedule | SH&E
- | Conduct Management Review | All Dept
- | Evaluation of Management Review Result | All Dept
- | Review and Evaluation HSE Activity Plan 2018 | SH&E
- | Conduct Corrective Action from Management Review Result (End of Year) | SH&E
| Total of Action Item Program (Jan) |  |  | 0
| Total of Compliance Action Item Program |  |  | #REF!
Jakarta, 29 January 2019
Prepared by
Leni Andani
SH&E Officer